## FULL LIST
Tier 1 | Tier 2 | Tier 3 | Description | Category
0000 |  |  | Enabling Works | Enabling Works
0000 | 0005 |  | Archaeology | Enabling Works
0000 | 0010 |  | Site Investigation | Enabling Works
0000 | 0010 | 0011 | Trial holes | Enabling Works
0000 | 0010 | 0012 | Soil testing | Enabling Works
0000 | 0100 |  | Demolition | Enabling Works
0000 | 0100 | 0101 | M&E Strip out | Enabling Works
0000 | 0100 | 0102 | Site strip / topsoil strip | Enabling Works
0000 | 0100 | 0103 | Hardstanding | Enabling Works
0000 | 0100 | 0104 | Invasive Plants | Enabling Works
0000 | 0100 | 0105 | Tree Felling / Arbor culturalist | Enabling Works
0000 | 0100 | 0110 | Façade Retention Scheme Removal | Enabling Works
0000 | 0100 | 0120 | Asbestos/Contaminates Removal | Enabling Works
0000 | 0200 |  | Site Establishment | Enabling Works
0000 | 0300 |  | Excavation and Piling Mat | Enabling Works
0000 | 0400 |  | Remediation | Enabling Works
0000 | 0500 |  | Temporary Works | Enabling Works
0000 | 0500 | 0501 | Temporary Structures | Enabling Works
0000 | 0500 | 0502 | Fencing (To Temporary Works and Structures) | Enabling Works
0000 | 0500 | 0503 | Protection of services | Enabling Works
0000 | 0500 | 0504 | Access Scaffolding | Enabling Works
0000 | 0500 | 0505 | Scaffolding - Support Scaffolding and Propping | Enabling Works
0000 | 0500 | 0506 | Temporary Piling | Enabling Works
0000 | 0500 | 0507 | Cofferdams | Enabling Works
0000 | 0500 | 0508 | Miscellaneous Temporary Works | Enabling Works
0000 | 0500 | 0509 | De-Watering | Enabling Works
0000 | 0500 | 0510 | Haul/Access roads | Enabling Works
0000 | 0700 |  | Service Diversions | Enabling Works
0000 | 0700 | 0705 | Service Diversions (BT) | Enabling Works
0000 | 0700 | 0710 | Service Diversions (Fibre) | Enabling Works
0000 | 0700 | 0715 | Service Diversions (Power) | Enabling Works
0000 | 0700 | 0720 | Service Diversions (Sewer) | Enabling Works
0000 | 0900 |  | Surveys | Enabling Works
0000 | 0900 | 0901 | Utility Mapping | Enabling Works
0000 | 0900 | 0902 | Magnometer Testing | Enabling Works
0000 |  | 0905 | Movement surveys | Enabling Works
0000 | 0900 | 0910 | Environmental Surveys/Monitoring | Enabling Works
0000 | 0900 | 0915 | Acoustic monitoring | Enabling Works
0000 | 0900 | 0920 | Services Surveys | Enabling Works
0000 | 0900 | 0926 | Service Validations | Enabling Works
0000 | 0900 | 0930 | Dilapidation Surveys | Enabling Works
0000 | 0900 | 0940 | Geotechnical Surveys | Enabling Works
1000 |  |  | Substructure | Substructure
1000 | 1010 |  | Earthworks | Substructure
1000 | 1010 | 1011 | Excavation | Substructure
1000 | 1010 | 1012 | Processing | Substructure
1000 | 1010 | 1013 | Deposition | Substructure
1000 | 1010 | 1014 | Disposal | Substructure
1000 | 1010 | 1015 | Import | Substructure
1000 | 1010 | 1016 | Compaction / preparation | Substructure
1000 | 1010 | 1017 | Topsoil (place) | Substructure
1000 | 1020 | 1025 | Drainage | Substructure
1000 | 1020 | 1026 | Land Drainage | Substructure
1000 | 1020 | 1027 | Ducts | Substructure
1000 | 1020 | 1028 | Surface Water Drainage | Substructure
1000 | 1020 | 1029 | Foul Water drainage | Substructure
1000 | 1020 | 1030 | Attenuation drainage/ponds | Substructure
1000 | 1020 | 1031 | Ditches and swales | Substructure
1000 | 1050 |  | Underpinning | Substructure
1000 | 1100 |  | Piling | Substructure
1000 | 1100 | 1120 | CFA Piling | Substructure
1000 | 1100 | 1130 | Vibro Piling / Vibro Compaction | Substructure
1000 | 1100 | 1150 | Driven / Sheet Piles | Substructure
1000 | 1100 | 1160 | Bored Piling | Substructure
1000 | 1100 | 1180 | Embedded Walls | Substructure
1000 | 1200 |  | Insitu Concrete | Substructure
1000 | 1200 | 1220 | Steel Fixing | Substructure
1000 | 1200 | 1240 | Formwork | Substructure
1000 | 1300 |  | Basement works | Substructure
1000 | 1300 | 1301 | Grouting | Substructure
1000 | 1500 |  | Groundwork | Substructure
1000 | 1520 |  | Gabions / Crib walling | Substructure
1000 | 1540 |  | Soil Nailing/Ground Anchors | Substructure
1000 | 1550 |  | Ground Stabilisation | Substructure
1000 | 1560 |  | Retaining walls | Substructure
1000 | 1570 |  | Reinforced Earth Walls / Embankments | Substructure
1000 | 1600 |  | Dewatering | Substructure
1000 | 1700 |  | Tunnelling/Shaft Work/Thrust Boring | Substructure
1000 | 1730 |  | Pipejacking | Substructure
1000 | 1800 |  | Gas Membrane | Substructure
1000 | 1850 |  | Waterproofing | Substructure
1000 | 1900 |  | Substructure Specialist Packages | Substructure
1000 | 1900 | 1901 | Lake Construction | Substructure
2000 |  |  | Superstructure | Superstructure
2000 | 2000 | 2001 | Structural Alterations | Superstructure
2000 | 2100 |  | Insitu Concrete Frame | Superstructure
2000 | 2110 |  | Insitu Concrete Floors/Slabs | Superstructure
2000 | 2120 |  | Pre-cast Concrete (Superstructure) | Superstructure
2000 | 2120 | 2121 | Precast Concrete - Sandwich Panels | Superstructure
2000 | 2120 | 2122 | Precast Concrete - Balconies | Superstructure
2000 | 2120 | 2123 | Precast Concrete - Twin Wall | Superstructure
2000 | 2120 | 2124 | Precast Concrete - Core Walls/ Boxes | Superstructure
2000 | 2120 | 2125 | Precast Concrete - Prestressed Solid Floor | Superstructure
2000 | 2120 | 2126 | Precast Concrete - Internal Solid Cross Walls | Superstructure
2000 | 2120 | 2127 | Precast Concrete - Stairs & Landings | Superstructure
| 2120 | 2128 | Precast Concrete - Beam and block flooring | Superstructure
2000 | 2130 |  | Precast Roof Units | Superstructure
2000 | 2140 |  | Formwork (Superstructure) | Superstructure
2000 | 2150 |  | Concrete Cutting and Coring | Superstructure
2000 | 2160 |  | Movement Joints/Bearings | Superstructure
2000 | 2180 |  | Post Tensioning | Superstructure
2000 | 2190 |  | Carbon Fibre Strengthening | Superstructure
2000 | 2200 |  | Structural Steelwork | Superstructure
2000 | 2210 |  | Light Gauge Metal Frame | Superstructure
2000 | 2220 |  | Metal Decking | Superstructure
2000 | 2240 |  | Secondary Steelwork | Superstructure
2000 | 2250 |  | Steel Framing System (SFS) | Superstructure
2000 | 2260 |  | Handrails / Balustrades | Superstructure
2000 | 2270 |  | Gantry's / Walkways | Superstructure
2000 | 2500 |  | Fire Protection | Superstructure
2000 | 2510 |  | Fire Protection Boarded | Superstructure
2000 | 2520 |  | Fire Protection Cementitious | Superstructure
2000 | 2530 |  | Fire Protection Intumescent | Superstructure
2000 | 2600 |  | Structural Timber | Superstructure
2000 | 2660 |  | Timber Stairs | Superstructure
2000 | 2670 |  | Metal Stairs | Superstructure
2000 | 2700 |  | Feature Stairs | Superstructure
2000 | 2800 |  | Concrete Repairs | Superstructure
2000 | 2900 |  | Conservation | Superstructure
2000 | 2900 | 2910 | Brickwork Conservation | Superstructure
2000 | 2900 | 2920 | External Joinery Conservation | Superstructure
3000 |  |  | Envelope | Envelope
3000 | 3050 |  | Brickwork/Blockwork | Envelope
3000 | 3050 | 3051 | Brick Slip | Envelope
3000 | 3140 |  | Masonry | Envelope
3000 | 3140 | 3141 | Stonework | Envelope
3000 | 3150 |  | Cavity Installation | Envelope
3000 | 3160 |  | Render | Envelope
3000 | 3160 | 3161 | Sto Render | Envelope
3000 | 3200 |  | Cladding | Envelope
3000 | 3200 | 3202 | Attendance Façade Survey | Envelope
3000 | 3200 | 3203 | Façade Restoration | Envelope
3000 | 3200 | 3204 | Cladding - Cleaning and Repairs | Envelope
3000 | 3200 | 3210 | Cladding - Unitised | Envelope
3000 | 3200 | 3220 | Cladding - Metal | Envelope
3000 | 3200 | 3230 | Cladding - Fibre Cement | Envelope
3000 | 3200 | 3240 | Cladding - PCC | Envelope
3000 | 3200 | 3250 | Cladding - GRC | Envelope
3000 | 3200 | 3260 | Cladding - Stone | Envelope
3000 | 3200 | 3265 | Cladding - Tiles | Envelope
3000 | 3200 | 3270 | Cladding - GRG | Envelope
3000 | 3200 | 3280 | Cladding - Timber | Envelope
3000 | 3200 | 3290 | Cladding - ETFE | Envelope
3000 | 3295 |  | Green/Living Wall | Envelope
3000 | 3300 |  | Rain Screen Cladding | Envelope
3000 | 3300 | 3310 | Rain Screen Masonry | Envelope
3000 | 3300 | 3320 | Rain Screen Metal | Envelope
3000 | 3300 | 3330 | Rain Screen Terracotta | Envelope
3000 | 3340 |  | Soffit Cladding | Envelope
3000 | 3350 |  | Masonry Cleaning/Repairs | Envelope
3000 | 3360 |  | Cladding - Fins | Envelope
3000 | 3380 |  | Plant Screens/Enclosures | Envelope
3000 | 3400 |  | Windows | Envelope
3000 | 3400 | 3410 | Windows Aluminium | Envelope
3000 | 3400 | 3420 | Windows Steel | Envelope
3000 | 3400 | 3430 | Windows Timber | Envelope
3000 | 3400 | 3440 | Window UPVC | Envelope
3000 | 3400 | 3450 | Glazing General | Envelope
3000 | 3400 | 3455 | Seconday Glazing | Envelope
3000 | 3400 | 3460 | Glass Block Walling | Envelope
3000 | 3400 | 3470 | Graphics / Manifestations | Envelope
3000 | 3500 |  | Curtain Walling Standard | Envelope
3000 | 3500 | 3501 | Curtain walling Stick | Envelope
3000 | 3500 | 3505 | Atrium Glazing | Envelope
3000 | 3510 |  | Glazing Patent | Envelope
3000 | 3550 |  | Structural Glazing | Envelope
3000 | 3600 |  | Louvres | Envelope
3000 | 3640 |  | Solar Shading | Envelope
3000 | 3660 |  | Facade Access Equipment | Envelope
3000 | 3800 |  | External Doors | Envelope
3000 | 3800 | 3810 | Doors - Timber | Envelope
3000 | 3800 | 3815 | Acoustic Fire Doors | Envelope
3000 | 3800 | 3820 | Doors - Metal | Envelope
3000 | 3800 | 3825 | Doors - Insulated Steel | Envelope
3000 | 3800 | 3830 | Loading Dock Gates | Envelope
3000 | 3800 | 3835 | Doors - Folding/Sliding | Envelope
3000 | 3800 | 3840 | Doors Automatic/Revolving | Envelope
3000 | 3800 | 3845 | Automatic Swing Door | Envelope
3000 | 3800 | 3850 | Distribution Network Operator Door Sets | Envelope
3000 | 3800 | 3860 | Doors Roller Shutters | Envelope
3000 | 3800 | 3870 | Doors Sectional Over Head | Envelope
3000 | 3800 | 3880 | Doors Rapid Riser | Envelope
3000 | 3800 | 3889 | Doors Strip Curtains | Envelope
3000 | 3800 | 3890 | Doors - Garage | Envelope
3000 | 3900 |  | Sealant Works | Envelope
3000 | 3950 |  | Balconies | Envelope
4000 |  |  | Roof | Roof
4000 | 4010 | 4011 | Roof - Bird Control | Roof
4000 | 4050 |  | Roof - Temporary Roofing/Waterproofing | Roof
4000 | 4100 |  | Roof - Metal | Roof
4000 | 4100 | 4101 | Roof - Zinc | Roof
4000 | 4100 | 4102 | Roof - Copper | Roof
4000 | 4100 | 4103 | Roof - Lead | Roof
4000 | 4100 | 4104 | Roof - Carbon Fibre | Roof
4000 | 4100 | 4105 | Roof - Copings | Roof
4000 | 4100 | 4106 | Roof - Main Finishes | Roof
4000 | 4100 | 4107 | Roof - Flat Finishes | Roof
4000 | 4150 |  | Roof Composite | Roof
4000 | 4200 |  | Roof Membrane/Single Ply | Roof
4000 | 4250 |  | Roof Asphalt | Roof
4000 | 4300 |  | Roof Green/Sedum | Roof
4000 | 4400 |  | Roof Tiled/Slate | Roof
4000 | 4450 |  | Lead Work | Roof
4000 | 4470 |  | Roof Features | Roof
4000 | 4470 | 4471 | Roof GRP Features | Roof
4000 | 4470 | 4472 | Roof Barriers | Roof
4000 | 4470 | 4473 | Roof - Glass Screens | Roof
4000 | 4500 |  | Roof Glazed | Roof
4000 | 4550 |  | Canopies Glass | Roof
4000 | 4560 |  | Canopies Fabric | Roof
4000 | 4600 |  | Roof Safety Access Systems | Roof
4000 | 4700 |  | Rainwater Systems & Goods | Roof
4000 | 4710 |  | Syphonic Roof Drainage | Roof
4000 | 4800 |  | Roof Lights | Roof
4000 | 4850 |  | Roof Smoke Vents | Roof
4000 | 4900 |  | Roof Insulation | Roof
4000 | 4910 |  | Soffit Insulation | Roof
5000 |  |  | M & E Services | M&E Services
5000 | 5010 | 5011 | Maintenance of Existing Services | M&E Services
5000 | 5100 |  | Electrical Services | M&E Services
5000 | 5100 | 5102 | Intelligent Electrical Services | M&E Services
5000 | 5100 | 5105 | Security/CCTV/Access | M&E Services
5000 | 5100 | 5106 | Photovoltaics | M&E Services
5000 | 5100 | 5107 | Lighting | M&E Services
5000 | 5100 | 5110 | Data/Voice | M&E Services
5000 | 5100 | 5115 | BMS/Controls | M&E Services
5000 | 5100 | 5120 | Fire & Safety | M&E Services
5000 | 5100 | 5125 | Lightning Protection | M&E Services
5000 | 5100 | 5130 | High Voltage | M&E Services
5000 | 5100 | 5135 | Audio Visual Equipment | M&E Services
5000 | 5100 | 5140 | PA Equipment | M&E Services
5000 | 5100 | 5145 | ICT Equipment | M&E Services
5000 | 5150 |  | Smart Buildings | M&E Services
5000 | 5150 | 5151 | Master System Architect | M&E Services
5000 | 5150 | 5152 | Network System Integrator | M&E Services
5000 | 5150 | 5153 | Monitoring | M&E Services
5000 | 5200 |  | Mechanical Services | M&E Services
5000 | 5200 | 5201 | Oil Tank | M&E Services
5000 | 5200 | 5202 | Medical Gas Installation | M&E Services
5000 | 5200 | 5205 | Plumbing | M&E Services
5000 | 5200 | 5210 | Sanitary ware | M&E Services
5000 | 5200 | 5215 | Sprinklers | M&E Services
5000 | 5200 | 5225 | Underfloor heating | M&E Services
5000 | 5200 | 5230 | Ductwork | M&E Services
5000 | 5200 | 5235 | Ventilation | M&E Services
5000 | 5200 | 5236 | Smoke Extraction | M&E Services
5000 | 5200 | 5240 | Ground Source Heat Pumps | M&E Services
5000 | 5300 |  | Drainage | M&E Services
5000 | 5300 | 5360 | Above Ground Drainage | M&E Services
5000 | 5300 | 5365 | Rising Main | M&E Services
5000 | 5300 | 5370 | Pumping Station | M&E Services
5000 | 5300 | 5380 | Water Features | M&E Services
5000 | 5400 |  | Swimming Pools/Spa | M&E Services
5000 | 5400 | 5401 | Pools | M&E Services
5000 | 5400 | 5402 | Jacuzzi | M&E Services
5000 | 5400 | 5403 | Sauna | M&E Services
5000 | 5600 |  | Utilities/External Services | M&E Services
5000 | 5600 | 5610 | Gas | M&E Services
5000 | 5600 | 5620 | Water | M&E Services
5000 | 5600 | 5630 | Electricity | M&E Services
5000 | 5600 | 5640 | Telephones | M&E Services
5000 | 5600 | 5650 | Data | M&E Services
5000 | 5600 | 5660 | Fire Main | M&E Services
5000 | 5600 | 5670 | Main Sewer Works | M&E Services
5000 | 5600 | 5680 | District Heating Works | M&E Services
5000 | 5700 |  | BWIC | M&E Services
5000 | 5900 |  | Commissioning | M&E Services
5000 | 5900 | 5901 | Witness Testing | M&E Services
5000 | 5900 | 5910 | Water Treatment | M&E Services
6000 | 6000 |  | Special Packages | Special Packages
6000 | 6000 | 6001 | Bathroom Pods | Special Packages
6000 | 6000 | 6002 | Accommodation | Special Packages
6000 | 6000 | 6003 | Room Pods | Special Packages
6000 | 6000 | 6004 | Mock Ups | Special Packages
6000 | 6000 | 6005 | Marketing Suite | Special Packages
6000 | 6000 | 6006 | Pre Fabricated Buildings | Special Packages
6000 | 6100 |  | Lifts | Special Packages
6000 | 6100 | 6101 | Passenger Lifts | Special Packages
6000 | 6100 | 6102 | Goods Lifts | Special Packages
6000 | 6100 | 6103 | Micro Lift and Dumb Waiters | Special Packages
6000 | 6100 | 6104 | Loading Bay Lifts | Special Packages
6000 | 6100 | 6110 | Lift Repairs and Maintenance | Special Packages
6000 | 6100 | 6111 | Testing Lifting Eyes | Special Packages
6000 | 6200 |  | Escalators | Special Packages
6000 | 6200 | 6250 | Materials Handling Equipment | Special Packages
6000 | 6200 | 6260 | Waste Chutes | Special Packages
6000 | 6200 | 6270 | Linen / Laundry Chutes | Special Packages
6000 | 6300 |  | Dock levellers | Special Packages
6000 | 6400 |  | Pest Control | Special Packages
6000 | 6500 |  | Fire Stopping | Special Packages
6000 | 6500 | 6510 | Fire Stopping (Specialist) | Special Packages
6000 | 6600 |  | Renovation | Special Packages
6000 | 6700 |  | Air Leakage Testing | Special Packages
6000 | 6700 | 6701 | VOC Testing | Special Packages
6000 | 6700 | 6702 | Acoustic Testing | Special Packages
6000 | 6700 | 6703 | Thermographic Testing | Special Packages
6000 | 6800 |  | Sports / auditoria | Special Packages
6000 | 6800 | 6801 | Seating | Special Packages
6000 | 6800 | 6802 | Staging | Special Packages
6000 | 6800 | 6803 | Line marking | Special Packages
6000 | 6800 | 6804 | Tennis Courts | Special Packages
6000 | 6800 | 6805 | Sports Equipment's | Special Packages
6000 | 6800 | 6806 | Squash Courts | Special Packages
6000 | 6800 | 6807 | Basketball Courts | Special Packages
6000 | 6800 | 6808 | Sports Pitches | Special Packages
6000 | 6800 | 6809 | Tensioned Grid | Special Packages
6000 | 6800 | 6810 | Theatre Production Lighting | Special Packages
6000 | 6800 | 6811 | Theatre Sound and Communications | Special Packages
6000 | 6850 |  | Building Cleaning Equipment | Special Packages
6000 | 6800 | 6851 | Window Cleaning Equipment - Bespoke | Special Packages
6000 | 6950 |  | Cranes and Hoists | Special Packages
7000 |  |  | Finishes | Finishes
7000 | 7005 |  | Heritage Works | Finishes
7000 | 7010 |  | Fire Places | Finishes
7000 | 7015 |  | Artisan Works | Finishes
7000 | 7020 |  | French Polishing and Damage Repairs | Finishes
7000 | 7025 |  | Acoustic Wall/Ceilings/Panels | Finishes
7000 | 7030 |  | Wall Finishes | Finishes
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7060 |  | Column Casing | Finishes
7000 | 7060 | 7061 | Column Casing - Composite | Finishes
7000 | 7070 |  | Partitions/Sliding/Folding | Finishes
7000 | 7100 |  | Plaster/Render | Finishes
7000 | 7100 | 7101 | Fibrous Plaster | Finishes
7000 | 7100 | 7102 | GRG Features | Finishes
7000 | 7100 | 7103 | Polished Plaster | Finishes
7000 | 7100 | 7104 | Acoustic Sprayed Plaster | Finishes
7000 | 7150 |  | Glazed Screens | Finishes
7000 | 7150 | 7155 | Glazed Screens Fire Related | Finishes
7000 | 7160 |  | Moveable Walls | Finishes
7000 | 7200 |  | Stone Finishes | Finishes
7000 | 7300 |  | Internal Doors | Finishes
7000 | 7300 | 7301 | Doors | Finishes
7000 | 7300 | 7302 | Ironmongery | Finishes
7000 | 7300 | 7303 | Sliding doors | Finishes
7000 | 7300 | 7304 | Specialist Theatre Doors | Finishes
7000 | 7340 |  | General Joinery | Finishes
7000 | 7380 |  | Special Joinery | Finishes
7000 | 7380 | 7381 | Kitchens | Finishes
7000 | 7380 | 7382 | Reception Desk | Finishes
7000 | 7380 | 7383 | Bed Head and Foot Walls (Medical) | Finishes
7000 | 7390 |  | Radiation Protection Walls | Finishes
7000 | 7390 | 7391 | Special Medical Bedroom / Bathroom Equipment | Finishes
7000 | 7390 | 7395 | Theatre Wall Finishes | Finishes
7000 | 7390 | 7396 | Clinical Vision Panels | Finishes
7000 | 7400 |  | Ceilings | Finishes
7000 | 7400 | 7401 | Monolithic Ceilings | Finishes
7000 | 7400 | 7402 | Suspended Ceilings | Finishes
7000 | 7400 | 7403 | Special Ceilings | Finishes
7000 | 7500 |  | Ceramic Tiling | Finishes
7000 | 7520 |  | Terrazzo | Finishes
7000 | 7520 | 7525 | Granite Floor Finish | Finishes
7000 | 7550 |  | Screeds | Finishes
7000 | 7550 | 7551 | Screeds - Epoxy/Resin | Finishes
7000 | 7550 | 7552 | Screeds - Isocrete | Finishes
7000 | 7600 |  | Raised Flooring | Finishes
7000 | 7620 |  | Timber Floors | Finishes
7000 | 7620 | 7621 | Timber Floors Sprung | Finishes
7000 | 7630 |  | Acoustic Floors | Finishes
7000 | 7640 |  | Floor Finishes | Finishes
7000 | 7640 | 7641 | Vinyl Floors | Finishes
7000 | 7640 | 7642 | Carpets | Finishes
7000 | 7640 | 7643 | Entrance/Matwell | Finishes
7000 | 7640 | 7644 | Flooring Repairs | Finishes
7000 | 7640 | 7645 | Rubber Flooring | Finishes
7000 | 7640 | 7646 | Liquid Applied Floor Finishes | Finishes
7000 | 7640 | 7646 | Sheet Floor Covering | Finishes
7000 | 7740 |  | Decorations | Finishes
7000 | 7750 |  | Hygienic Wall Cladding | Finishes
7000 | 7760 |  | Mirrors | Finishes
7000 | 7770 |  | Wall Protection | Finishes
7000 | 7770 | 7771 | Wall Protection - Rubber | Finishes
7000 | 7800 |  | Metalwork | Finishes
7000 | 7800 | 7801 | Metal Gratings | Finishes
7000 | 7840 |  | Architectural Metalwork | Finishes
7000 | 7860 |  | Fire Shutters/Smoke Screen | Finishes
7000 | 7860 | 7861 | Fire Curtains | Finishes
7000 | 7900 |  | Toilet Cubicles / IPS | Finishes
7000 | 7940 |  | Blinds | Finishes
7000 | 7950 |  | Access Hatches | Finishes
7000 | 7960 |  | Signage (Internal) | Finishes
7000 | 7970 |  | Sauna & Jacuzzi | Finishes
7000 | 7980 |  | Furniture/Fittings | Finishes
7000 | 7980 | 7981 | Feature Lighting | Finishes
7000 | 7990 |  | Display Screens | Finishes
8000 |  |  | External Works | External Works
8000 | 8070 |  | Pond Liners / Swales | External Works
8000 | 8080 |  | SUDS Systems | External Works
8000 | 8100 |  | Highway Works | External Works
8000 | 8100 | 8101 | 278 works | External Works
8000 | 8100 | 8102 | Road Markings | External Works
8000 | 8100 | 8103 | Car Park Floor Markings | External Works
8000 | 8100 | 8104 | Automatic Car Parking System | External Works
8000 | 8100 | 8110 | Car Park | External Works
8000 | 8150 |  | Traffic Management | External Works
8000 | 8150 | 8151 | Establish & Remove Traffic Management | External Works
8000 | 8150 | 8152 | Maintain Traffic Management | External Works
8000 | 8150 | 8153 | Establish and Remove Traffic Diversions (public) | External Works
8000 | 8150 | 8154 | Maintain Traffic Diversions (public) | External Works
8000 | 8150 | 8155 | Establish & Remove Recovery | External Works
8000 | 8150 | 8156 | Maintenance of Recovery Vehicle | External Works
8000 | 8150 | 8157 | Temporary speed enforcement cameras - set-up, maintenance, monitoring and removal | External Works
8000 | 8150 | 8158 | Temporary CCTV - set-up, maintenance, monitoring and removal | External Works
8000 | 8200 |  | Civil Works | External Works
8000 | 8200 | 8220 | Road Surfacing | External Works
8000 | 8300 |  | Bridges | External Works
8000 | 8300 | 8310 | Concrete Bridges | External Works
8000 | 8300 | 8320 | Timber Bridges | External Works
8000 | 8400 |  | Hard Landscaping | External Works
8000 | 8400 | 8410 | Retaining walls | External Works
8000 | 8400 | 8450 | Soft Landscaping/Planting | External Works
8000 | 8400 | 8451 | Landscaping - Irrigation | External Works
8000 | 8500 |  | Fencing | External Works
8000 | 8500 | 8501 | Road Restraint Systems | External Works
8000 | 8500 | 8502 | Palisade Fencing | External Works
8000 | 8500 | 8503 | Paladin Fencing | External Works
8000 | 8500 | 8504 | Security (RZ) Fencing | External Works
8000 | 8500 | 8505 | Timber Fencing | External Works
8000 | 8500 | 8506 | Acoustic fencing/barrier | External Works
8000 | 8510 |  | Barriers | External Works
8000 | 8520 |  | Turnstiles | External Works
8000 | 8550 |  | Gates | External Works
8000 | 8550 | 8551 | Gates - Timber | External Works
8000 | 8550 | 8552 | Gates - Iron | External Works
8000 | 8550 | 8553 | Gates - Automation | External Works
8000 | 8600 |  | Walls | External Works
8000 | 8700 |  | Furniture / Features | External Works
8000 | 8700 | 8701 | External furniture / street furniture | External Works
8000 | 8700 | 8702 | External Features | External Works
8000 | 8700 | 8703 | Cycle Stores / Hoops | External Works
8000 | 8700 | 8704 | Bat Housing | External Works
8000 | 8900 |  | Signage (External) | External Works
8000 | 8950 |  | Metalwork | External Works
8000 | 8960 |  | Ecological Works | External Works
9000 |  |  | Fitting Out | Fitting Out
9000 | 9100 |  | Furniture Fittings & Equipment | Fitting Out
9000 | 9100 | 9102 | Cold Room Fit Out | Fitting Out
9000 | 9100 | 9103 | Kitchen Fit Out | Fitting Out
9000 | 9100 | 9104 | Washroom Fit Out | Fitting Out
9000 | 9100 | 9110 | Kitchen Equipment | Fitting Out
9000 | 9100 | 9111 | High Density Storage | Fitting Out
9000 | 9100 | 9112 | Task Seating | Fitting Out
9000 | 9100 | 9113 | Storage Cabinets | Fitting Out
9000 | 9100 | 9114 | Soft Seating | Fitting Out
9000 | 9100 | 9115 | Hard Seating & Tables | Fitting Out
9000 | 9100 | 9116 | Office Equipment | Fitting Out
9000 | 9100 | 9117 | Legacy Equipment | Fitting Out
9000 | 9100 | 9118 | White Goods | Fitting Out
9000 | 9100 | 9119 | Lockers | Fitting Out
9000 | 9100 | 9120 | Mailboxes | Fitting Out
9000 | 9200 |  | Decant | Fitting Out
9000 | 9400 |  | CAT A Fit Out | Fitting Out
9000 | 9500 |  | CAT B Fit Out | Fitting Out
9000 | 9600 |  | Remedial Works | Fitting Out
9000 | 9850 |  | Cleanrooms | Fitting Out
9000 | 9900 |  | Laboratory Equipment | Fitting Out
10000 | 10000 |  | Direct Works | Direct Works
10000 | 10001 |  | Labour | Direct Works
10000 | 10002 |  | Plant | Direct Works
10000 | 10003 |  | Materials | Direct Works
11000 |  |  | Suppliers | Suppliers
11000 | 11005 |  | Aggregates | Suppliers
11000 | 11010 | 11010 | Brick & Block | Suppliers
11000 | 11010 | 11011 | Facing Bricks | Suppliers
11000 | 11010 | 11012 | Concrete Blocks | Suppliers
11000 | 11010 | 11013 | Brickwork Accessories | Suppliers
11000 | 11010 | 11014 | Ready mix mortar | Suppliers
11000 | 11010 | 11015 | Lintels | Suppliers
11000 | 11020 | 11020 | Drainage | Suppliers
11000 | 11020 | 11021 | Internal drainage | Suppliers
11000 | 11020 | 11022 | External Drainage | Suppliers
11000 | 11020 | 11023 | Concrete Drainage | Suppliers
11000 | 11020 | 11024 | Kerbs / Channel drains | Suppliers
11000 | 11030 |  | Road kerbs & paving | Suppliers
11000 | 11035 |  | Street Furniture | Suppliers
11000 | 11040 |  | Manhole Covers & Castings | Suppliers
11000 | 11050 |  | Reinforcement | Suppliers
11000 | 11050 | 11051 | Cut & Bent rebar | Suppliers
11000 | 11050 | 11052 | Fabric reinforcement | Suppliers
11000 | 11050 | 11053 | Rebar | Suppliers
11000 | 11050 | 11055 | Insulation | Suppliers
11000 | 11060 |  | Joinery Products | Suppliers
11000 | 11060 | 11061 | Internal Doors & Screens | Suppliers
11000 | 11060 | 11062 | Timber & Sheet products | Suppliers
11000 | 11060 | 11063 | Toilet cubicles | Suppliers
11000 | 11060 | 11075 | Ironmongery | Suppliers
11000 | 11080 |  | Partitioning & Dry lining | Suppliers
11000 | 11080 | 11081 | Plasterboard | Suppliers
11000 | 11080 | 11082 | Metal stud/MFS | Suppliers
11000 | 11080 | 11083 | Accessories | Suppliers
11000 | 11080 | 11084 | Suspended Ceilings | Suppliers
11000 | 11080 | 11085 | Chemicals & Consumables | Suppliers
11000 | 11090 |  | Metalwork, Fixings & Fasteners | Suppliers
11000 | 11090 | 11095 | Waterproofing | Suppliers
11000 | 11090 | 11096 | Damp proof membrane | Suppliers
11000 | 11090 | 11097 | Tanking | Suppliers
12000 |  |  | Healthcare | Healthcare
12000 | 12010 |  | Nurse Call System | Healthcare
12000 | 12020 |  | Staff Attack System | Healthcare
12000 | 12030 |  | Ultra Clean Ventilation | Healthcare
12000 | 12040 |  | Surgical Lights | Healthcare
12000 | 12050 |  | Medical Hoists | Healthcare
12000 | 12060 |  | MRI Ferrous Detectors | Healthcare
12000 | 12070 |  | Imaging | Healthcare
12000 | 12070 | 12071 | Imaging - X-Ray | Healthcare
12000 | 12070 | 12072 | Imaging - Hybrid Theatre | Healthcare
12000 | 12070 | 12073 | Imaging - Surgeons Cameras | Healthcare
12000 | 12070 | 12074 | Dirty Utility Room Macerators | Healthcare
12000 | 12080 |  | Pharmacy | Healthcare
12000 | 12080 | 12081 |  | Healthcare
12000 | 12080 | 12082 | Pharmacy Dispensing Robot | Healthcare
12000 | 12080 | 12083 | Drugs Cabinet | Healthcare
12000 | 12090 |  | Medical Equipment | Healthcare

## Building 1
Tier 1 | Tier 2 | Tier 3 | Description | Category
0000 | 0100 |  | Demolition | Enabling Works
1000 | 1100 |  | Piling | Substructure
2000 | 2100 |  | Insitu Concrete Frame | Superstructure
2000 | 2200 |  | Structural Steelwork | Superstructure
3000 | 3050 |  | Brickwork/Blockwork | Envelope
3000 | 3200 |  | Cladding | Envelope
3000 | 3500 | 3502 | Wintergarden | Envelope
3000 | 3660 |  | Facade Access Equipment | Envelope
4000 | 4200 |  | Roof Membrane/Single Ply | Roof
5000 | 5100 |  | Electrical Services | M&E Services
5000 | 5150 |  | Smart Buildings | M&E Services
5000 | 5200 |  | Mechanical Services | M&E Services
5000 | 5200 | 5236 | Smoke Extraction | M&E Services
5000 | 5600 |  | Utilities/External Services | M&E Services
5000 | 5700 |  | BWIC | M&E Services
5000 | 5900 |  | Commissioning | M&E Services
6000 | 6100 |  | Lifts | Special Packages
6000 | 6700 |  | Air Leakage Testing | Special Packages
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7200 |  | Stone Finishes | Finishes
7000 | 7340 |  | General Joinery | Finishes
7000 | 7600 |  | Raised Flooring | Finishes
7000 | 7640 |  | Floor Finishes | Finishes
7000 | 7740 |  | Decorations | Finishes
7000 | 7800 |  | Metalwork | Finishes
8000 | 8400 |  | Hard Landscaping | External Works
8000 | 8400 | 8450 | Soft Landscaping/Planting | External Works
8000 | 8700 | 8702 | External Features | External Works
8000 | 8900 |  | Signage (External) | External Works
9000 | 9100 |  | Furniture Fittings & Equipment | Fitting Out
9000 | 9100 | 9104 | Washroom Fit Out | Fitting Out

## Building 2
Tier 1 | Tier 2 | Tier 3 | Description | Category
1000 | 1100 | 1120 | CFA Piling | Substructure
1000 | 1500 |  | Groundwork | Substructure
2000 | 2200 |  | Structural Steelwork | Superstructure
2000 | 2500 |  | Fire Protection | Superstructure
2000 | 2600 |  | Structural Timber | Superstructure
3000 | 3050 |  | Brickwork/Blockwork | Envelope
3000 | 3160 |  | Render | Envelope
3000 | 3400 |  | Windows & Glazing | Envelope
3000 | 3400 | 3420 | Windows Steel | Envelope
3000 | 3500 |  | Curtain Walling Standard | Envelope
4000 | 4200 |  | Roof Membrane/Single Ply | Roof
4000 | 4200 |  | Roof Membrane/Single Ply | Roof
4000 | 4250 |  | Roof Asphalt | Roof
4000 | 4700 |  | Rainwater Systems & Goods | Roof
4000 | 4800 |  | Roof Lights | Roof
4000 | 4850 |  | Roof Smoke Vents | Roof
5000 |  |  | M & E Services | M&E Services
5000 | 5100 | 5125 | Lightning Protection | M&E Services
5000 | 5600 | 5630 | Electricity | M&E Services
5000 | 5700 |  | BWIC | M&E Services
6000 | 6000 | 6001 | Bathroom Pods | Special Packages
6000 | 6100 |  | Lifts | Special Packages
6000 | 6500 |  | Fire Stopping | Special Packages
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7100 |  | Plaster/Render | Finishes
7000 | 7150 |  | Glazed Screens | Finishes
7000 | 7300 | 7301 | Doors | Finishes
7000 | 7500 |  | Ceramic Tiling | Finishes
7000 | 7550 |  | Screeds | Finishes
7000 | 7640 |  | Floor Finishes | Finishes
7000 | 7740 |  | Decorations | Finishes
7000 | 7760 |  | Mirrors | Finishes
7000 | 7770 |  | Wall Protection | Finishes
7000 | 7840 |  | Architectural Metalwork | Finishes
7000 | 7940 |  | Blinds | Finishes
7000 | 7960 |  | Signage (Internal) | Finishes
9000 | 9100 |  | Furniture Fittings & Equipment | Fitting Out
9000 | 9100 |  | Furniture Fittings & Equipment | Fitting Out

## Building 3
Tier 1 | Tier 2 | Tier 3 | Description | Category
0000 | 0100 | 0105 | Tree Felling / Arboriculturalist | Enabling Works
0000 | 0500 | 0510 | Haul/Access roads | Enabling Works
1000 | 1010 |  | Earthworks | Substructure
1000 | 1020 | 1025 | Drainage | Substructure
1000 | 1020 | 1029 | Foul Water drainage | Substructure
1000 | 1020 | 1031 | Ditches and swales | Substructure
1000 | 1500 |  | Groundwork | Substructure
1000 | 1550 |  | Ground Stabilisation | Substructure
2000 | 2100 |  | Insitu Concrete Frame | Superstructure
2000 | 2200 |  | Structural Steelwork | Superstructure
3000 | 3050 |  | Brickwork/Blockwork | Envelope
3000 | 3200 | 3220 | Cladding - Metal | Envelope
3000 | 3200 | 3240 | Cladding - PCC | Envelope
3000 | 3400 | 3450 | Glazing General | Envelope
3000 | 3500 |  | Curtain Walling Standard | Envelope
3000 | 3640 |  | Solar Shading | Envelope
4000 | 4250 |  | Roof Asphalt | Roof
4000 | 4800 |  | Roof Lights | Roof
5000 |  |  | M & E Services | M&E Services
5000 | 5200 | 5240 | Ground Source Heat Pumps | M&E Services
5000 | 5600 | 5610 | Gas | M&E Services
5000 | 5600 | 5630 | Electricity | M&E Services
5000 | 5600 | 5620 | Water | M&E Services
5000 | 5600 | 5630 | Electricity | M&E Services
5000 | 5600 | 5670 | Main Sewer Works | M&E Services
6000 | 6000 | 6004 | Mock Ups | Special Packages
6000 | 6500 | 6510 | Fire Stopping (Specialist) | Special Packages
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7150 |  | Glazed Screens | Finishes
7000 | 7340 |  | General Joinery | Finishes
7000 | 7380 | 7381 | Kitchens | Finishes
7000 | 7500 |  | Ceramic Tiling | Finishes
7000 | 7550 |  | Screeds | Finishes
7000 | 7600 |  | Raised Flooring | Finishes
7000 | 7640 |  | Floor Finishes | Finishes
7000 | 7740 |  | Decorations | Finishes
7000 | 7750 |  | Hygienic Wall Cladding | Finishes
7000 | 7840 |  | Architectural Metalwork | Finishes
7000 | 7860 |  | Fire Shutters/Smoke Screen | Finishes
8000 | 8400 | 8450 | Soft Landscaping/Planting | External Works
8000 | 8900 |  | Signage (External) | External Works
8000 | 8960 |  | Ecological Works | External Works

## Building 4
Tier 1 | Tier 2 | Tier 3 | Description | Category
0000 |  |  | Enabling Works | Enabling Works
0000 | 0010 |  | Site Investigation | Enabling Works
0000 | 0100 |  | Demolition | Enabling Works
0000 | 0100 | 0105 | Tree Felling / Arbor culturalist | Enabling Works
0000 | 0200 |  | Site Establishment | Enabling Works
0000 | 0300 |  | Excavation and Piling Mat | Enabling Works
0000 | 0500 |  | Temporary Works | Enabling Works
0000 | 0500 | 0504 | Access Scaffolding | Enabling Works
0000 | 0700 |  | Service Diversions | Enabling Works
0000 | 0900 |  | Surveys | Enabling Works
0000 |  | 0905 | Movement surveys | Enabling Works
0000 | 0900 | 0910 | Environmental Surveys/Monitoring | Enabling Works
0000 | 0900 | 0915 | Acoustic monitoring | Enabling Works
0000 | 0900 | 0930 | Dilapidation Surveys | Enabling Works
1000 | 1010 |  | Earthworks | Substructure
1000 | 1020 | 1025 | Drainage | Substructure
1000 | 1050 |  | Underpinning | Substructure
1000 | 1100 |  | Piling | Substructure
1000 | 1200 |  | Insitu Concrete | Substructure
2000 | 2110 |  | Insitu Concrete Floors/Slabs | Superstructure
2000 | 2120 | 2127 | Precast Concrete - Stairs & Landings | Superstructure
2000 | 2200 |  | Structural Steelwork | Superstructure
2000 | 2240 |  | Secondary Steelwork | Superstructure
2000 | 2250 |  | Steel Framing System (SFS) | Superstructure
2000 | 2270 |  | Gantry's / Walkways | Superstructure
3000 | 3050 |  | Brickwork/Blockwork | Envelope
3000 | 3200 | 3220 | Cladding - Metal | Envelope
3000 | 3400 | 3410 | Windows Aluminium | Envelope
3000 | 3500 |  | Curtain Walling Standard | Envelope
3000 | 3800 | 3820 | Doors - Metal | Envelope
4000 | 4150 |  | Roof Composite | Roof
5000 |  |  | M & E Services | M&E Services
5000 | 5600 |  | Utilities/External Services | M&E Services
5000 | 5700 |  | BWIC | M&E Services
6000 | 6100 |  | Lifts | Special Packages
6000 | 6100 | 6102 | Goods Lifts | Special Packages
6000 | 6100 | 6103 | Micro Lift and Dumb Waiters | Special Packages
6000 | 6500 |  | Fire Stopping | Special Packages
6000 | 6700 |  | Air Leakage Testing | Special Packages
6000 | 6700 | 6702 | Acoustic Testing | Special Packages
6000 | 6800 | 6801 | Seating | Special Packages
6000 | 6800 | 6802 | Staging | Special Packages
6000 | 6800 | 6810 | Theatre Production Lighting | Special Packages
6000 | 6800 | 6811 | Theatre Sound and Communications | Special Packages
7000 | 7030 |  | Wall Finishes | Finishes
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7100 |  | Plaster/Render | Finishes
7000 | 7150 |  | Glazed Screens | Finishes
7000 | 7160 |  | Moveable Walls | Finishes
7000 | 7200 |  | Stone Finishes | Finishes
7000 | 7340 |  | General Joinery | Finishes
7000 | 7380 |  | Special Joinery | Finishes
7000 | 7380 | 7381 | Kitchens | Finishes
7000 | 7400 | 7402 | Suspended Ceilings | Finishes
7000 | 7400 | 7403 | Special Ceilings | Finishes
7000 | 7500 |  | Ceramic Tiling | Finishes
7000 | 7520 |  | Terrazzo | Finishes
7000 | 7550 |  | Screeds | Finishes
7000 | 7620 |  | Timber Floors | Finishes
7000 | 7640 | 7641 | Vinyl Floors | Finishes
7000 | 7640 | 7643 | Entrance/Matwell | Finishes
7000 | 7740 |  | Decorations | Finishes
7000 | 7840 |  | Architectural Metalwork | Finishes
7000 | 7900 |  | Toilet Cubicles / IPS | Finishes
7000 | 7940 |  | Blinds | Finishes
7000 | 7960 |  | Signage (Internal) | Finishes
7000 | 7980 |  | Furniture/Fittings | Finishes
8000 | 8400 |  | Hard Landscaping | External Works
8000 | 8400 | 8450 | Soft Landscaping/Planting | External Works
8000 | 8700 | 8701 | External furniture / street furniture | External Works

## Building 5
Tier 1 | Tier 2 | Tier 3 | Description | Category
0000 | 0500 | 0504 | Access Scaffolding | Enabling Works
1000 | 1200 |  | Insitu Concrete | Substructure
2000 | 2000 | 2001 | Structural Alterations | Superstructure
2000 | 2200 |  | Structural Steelwork | Superstructure
2000 | 2250 |  | Steel Framing System (SFS) | Superstructure
2000 | 2500 |  | Fire Protection | Superstructure
2000 | 2600 |  | Structural Timber | Superstructure
2000 | 2700 |  | Feature Stairs | Superstructure
3000 | 3050 |  | Brickwork/Blockwork | Envelope
3000 | 3200 | 3203 | Façade Restoration | Envelope
3000 | 3200 | 3260 | Cladding - Stone | Envelope
3000 | 3340 |  | Soffit Cladding | Envelope
3000 | 3380 |  | Plant Screens/Enclosures | Envelope
3000 | 3800 | 3810 | Doors - Timber | Envelope
3000 | 3800 | 3820 | Doors - Metal | Envelope
3000 | 3800 | 3840 | Doors Automatic/Revolving | Envelope
4000 | 4100 | 4107 | Roof - Flat Finishes | Roof
4000 | 4200 |  | Roof Membrane/Single Ply | Roof
4000 | 4400 |  | Roof Tiled/Slate | Roof
4000 | 4450 |  | Lead Work | Roof
4000 | 4470 |  | Roof Features | Roof
4000 | 4600 |  | Roof Safety Access Systems | Roof
5000 |  |  | M & E Services | M&E Services
5000 | 5100 | 5105 | Security/CCTV/Access | M&E Services
5000 | 5100 | 5120 | Fire & Safety | M&E Services
5000 | 5100 | 5125 | Lightning Protection | M&E Services
5000 | 5100 | 5135 | Audio Visual Equipment | M&E Services
5000 | 5200 | 5215 | Sprinklers | M&E Services
5000 | 5200 | 5236 | Smoke Extraction | M&E Services
5000 | 5400 |  | Swimming Pools/Spa | M&E Services
5000 | 5700 |  | BWIC | M&E Services
6000 | 6100 |  | Lifts | Special Packages
7000 | 7025 |  | Acoustic Wall/Ceilings/Panels | Finishes
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7150 |  | Glazed Screens | Finishes
7000 | 7620 |  | Timber Floors | Finishes
7000 | 7640 |  | Floor Finishes | Finishes
7000 | 7740 |  | Decorations | Finishes
7000 | 7800 |  | Metalwork | Finishes
7000 | 7840 |  | Architectural Metalwork | Finishes
7000 | 7860 | 7861 | Fire Curtains | Finishes
8000 | 8400 |  | Hard Landscaping | External Works
8000 | 8400 | 8450 | Soft Landscaping/Planting | External Works
9000 |  |  | Fitting Out | Fitting Out
9000 | 9100 |  | Furniture Fittings & Equipment | Fitting Out
9000 | 9100 | 9103 | Kitchen Fit Out | Fitting Out

## Building 6
Tier 1 | Tier 2 | Tier 3 | Description | Category
0000 | 0100 |  | Demolition | Enabling Works
0000 | 0200 |  | Site Establishment | Enabling Works
0000 | 0500 | 0504 | Access Scaffolding | Enabling Works
1000 | 1200 |  | Insitu Concrete | Substructure
2000 | 2200 |  | Structural Steelwork | Superstructure
2000 | 2240 |  | Secondary Steelwork | Superstructure
3000 | 3050 |  | Brickwork/Blockwork | Envelope
3000 | 3400 |  | Windows | Envelope
3000 | 3900 |  | Sealant Works | Envelope
4000 |  |  | Roof | Roof
5000 |  |  | M & E Services | M&E Services
5000 | 5200 | 5202 | Medical Gas Installation | M&E Services
5000 | 5400 | 5401 | Pools | M&E Services
5000 | 5900 |  | Commissioning | M&E Services
6000 | 6500 |  | Fire Stopping | Special Packages
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7300 |  | Internal Doors | Finishes
7000 | 7380 | 7382 | Reception Desk | Finishes
7000 | 7640 |  | Floor Finishes | Finishes
7000 | 7740 |  | Decorations | Finishes
7000 | 7750 |  | Hygienic Wall Cladding | Finishes
7000 | 7770 |  | Wall Protection | Finishes
7000 | 7840 |  | Architectural Metalwork | Finishes
7000 | 7900 |  | Toilet Cubicles / IPS | Finishes
7000 | 7940 |  | Blinds | Finishes
7000 | 7980 |  | Furniture/Fittings | Finishes
8000 | 8900 |  | Signage (External) | External Works
12000 | 12090 |  | Medical Equipment | Healthcare

## Building 7
Tier 1 | Tier 2 | Tier 3 | Description | Category
1000 | 1500 |  | Groundwork | Substructure
1000 | 1850 |  | Waterproofing | Substructure
3000 | 3050 |  | Brickwork/Blockwork | Envelope
3000 | 3200 | 3220 | Cladding - Metal | Envelope
3000 | 3200 | 3260 | Cladding - Stone | Envelope
3000 | 3550 |  | Structural Glazing | Envelope
3000 | 3660 |  | Facade Access Equipment | Envelope
4000 | 4300 |  | Roof Green/Sedum | Roof
5000 |  |  | M & E Services | M&E Services
5000 | 5100 | 5125 | Lightning Protection | M&E Services
5000 | 5900 |  | Commissioning | M&E Services
6000 | 6100 |  | Lifts | Special Packages
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7340 |  | General Joinery | Finishes
7000 | 7500 |  | Ceramic Tiling | Finishes
7000 | 7740 |  | Decorations | Finishes
7000 | 7840 |  | Architectural Metalwork | Finishes
7000 | 7960 |  | Signage (Internal) | Finishes
8000 | 8100 | 8103 | Car Park Floor Markings | External Works
8000 | 8400 |  | Hard Landscaping | External Works

## Building 8
Tier 1 | Tier 2 | Tier 3 | Description | Category
0000 | 0900 | 0915 | Acoustic monitoring | Enabling Works
2000 | 2240 |  | Secondary Steelwork | Superstructure
3000 | 3900 |  | Sealant Works | Envelope
5000 |  |  | M & E Services | M&E Services
5000 | 5100 | 5135 | Audio Visual Equipment | M&E Services
5000 | 5700 |  | BWIC | M&E Services
6000 | 6000 | 6001 | Bathroom Pods | Special Packages
6000 | 6000 | 6004 | Mock Ups | Special Packages
6000 | 6100 | 6103 | Micro Lift and Dumb Waiters | Special Packages
6000 | 6500 |  | Fire Stopping | Special Packages
7000 | 7050 |  | Partitions/Dry Lining & Ceilings | Finishes
7000 | 7070 |  | Partitions/Sliding/Folding | Finishes
7000 | 7100 |  | Plaster/Render | Finishes
7000 | 7340 |  | General Joinery | Finishes
7000 | 7500 |  | Ceramic Tiling | Finishes
7000 | 7550 |  | Screeds | Finishes
7000 | 7640 | 7641 | Vinyl Floors | Finishes
7000 | 7640 | 7642 | Carpets | Finishes
7000 | 7740 |  | Decorations | Finishes
| 7840 |  | Architectural Metalwork | Finishes
7000 | 7940 |  | Blinds | Finishes
7000 | 7960 |  | Signage (Internal) | Finishes
8000 | 8900 |  | Signage (External) | External Works
9000 |  |  | Fitting Out (Level 21 & 22 Fit Out) | Fitting Out
9000 |  |  | Fitting Out (Level 7) | Fitting Out
9001 |  |  | Linen Chute | Fitting Out
9000 | 9100 |  | Furniture Fittings & Equipment | Fitting Out
9000 | 9100 | 9110 | Kitchen Equipment | Fitting Out

## Building 9
Tier 1 | Tier 2 | Tier 3 | Description | Category
0000 |  |  | Enabling Works | Enabling Works
0000 | 0100 |  | Demolition | Enabling Works
0000 | 0100 | 0120 | Asbestos/Contaminates Removal | Enabling Works
1000 |  |  | Substructure | Substructure
|  | 1120 | CFA Piling | Substructure
1000 | 1100 | 1150 | Driven / Sheet Piles | Substructure
2000 | 2100 |  | Insitu Concrete Frame | Superstructure
2000 | 2200 |  | Structural Steelwork | Superstructure
2001 | 2200 |  | Structural Steelwork | Superstructure
2002 | 2200 |  | Structural Steelwork | Superstructure
2000 | 2200 |  | Structural Steelwork | Superstructure
2001 | 2240 |  | Secondary Steelwork | Superstructure
2002 | 2240 |  | Secondary Steelwork | Superstructure
2000 | 2260 |  | Handrails / Balustrades | Superstructure
| 2260 |  | Handrails / Balustrades | Superstructure
3000 | 3050 |  | Brickwork/Blockwork | Envelope
3000 | 3160 | 3161 | Sto Render | Envelope
3000 | 3200 | 3220 | Cladding - Metal | Envelope
3000 | 3200 | 3240 | Cladding - PCC | Envelope
3000 | 3200 | 3260 | Cladding - Stone | Envelope
3000 | 3300 |  | Rain Screen Cladding | Envelope
3000 | 3320 |  | Rain Screen Metal | Envelope
3000 | 3380 |  | Plant Screens/Enclosures | Envelope
3000 | 3500 |  | Curtain Walling Standard | Envelope
3000 | 3550 |  | Structural Glazing | Envelope
3000 | 3600 |  | Louvres | Envelope
3000 | 3660 |  | Facade Access Equipment | Envelope
4000 | 4910 |  | Soffit Insulation | Roof
5000 |  |  | M & E Services | M&E Services
5000 |  |  | M & E Services | M&E Services
5000 | 5100 | 5125 | Lightning Protection | M&E Services
5000 | 5300 | 5380 | Water Features | M&E Services
5000 | 5700 |  | BWIC | M&E Services
5000 | 5900 |  | Commissioning | M&E Services
6000 | 6100 |  | Lifts | Special Packages
6000 | 6100 | 6101 | Passenger Lifts | Special Packages
6000 | 6100 | 6102 | Goods Lifts | Special Packages
6000 | 6500 |  | Fire Stopping | Special Packages
6000 | 6700 |  | Air Leakage Testing | Special Packages
7000 | 7050 |  | Partitions/Dry Lining | Finishes
7000 | 7100 |  | Plaster/Render | Finishes
7000 | 7340 |  | General Joinery | Finishes
7000 | 7500 |  | Ceramic Tiling | Finishes
7000 | 7520 |  | Terrazzo | Finishes
7000 | 7550 |  | Screeds | Finishes
7000 | 7640 |  | Floor Finishes | Finishes
7000 | 7740 |  | Decorations | Finishes
7000 | 7900 |  | Toilet Cubicles / IPS | Finishes
7000 | 7960 |  | Signage (Internal) | Finishes
7000 | 7980 |  | Furniture/Fittings | Finishes
8000 | 8100 | 8103 | Car Park Floor Markings | External Works
8000 | 8400 |  | Hard Landscaping | External Works
8000 | 8400 | 8450 | Soft Landscaping/Planting | External Works
8000 | 8510 |  | Barriers | External Works
11000 |  | 11022 | External Drainage | Suppliers